## Const. Phase
University of Illinois |  |  |  |  | Instructions:
CONTRACTOR EVALUATION |  |  |  |  | Boxes highlighted in blue require input from the evaluator.
CONSTRUCTION PHASE |  |  |  |  | Normally completed at Substantial Completion, but may be used during construction as means to provide feedback to contract areas of poor performance
Project Name: |  |  | Date: |  | Complete the project specific data, date and your name.
Project Location: |  |  | UI Project #:
CDB Project #:
Evaluator Name: |  |  | Contractor Name:
Surveyor Name: |  |  |  |  | The quantitative section should be completed prior to the qualitative. Provide the quantitative measurements to any project team members requested to complete an evaluation. If this is an "Advisory" Evaluation the Quantitative Measurement do not need to be filled out.
QUANTITATIVE MEASUREMENTS:
1 | Original Total Construction Contract Amount: |  |  |  | The total contract amount for construction for this Contractors portion of work.
2 | Number of Change Orders Issued: |  |  |  | Information from PRZM
3 | Total Dollar Value of Change Orders (CO): |  |  |  | Information from PRZM
4 | Percentage of CO to Total Contract Amount: |  |  | #DIV/0! | This number will be automatically generated.
5 | Total Dollar Value of Liquidated Damages Assessed: |  |  |  | Information from PRZM
6 | Notice to Proceed Start Date: |  |  |  | The start date indicated on the Notice to Proceed letter.
7 | Original Date of Substantial Completion: |  |  |  | The date provided by the Contractor's original schedule (or approved revised schedule).
Revised Substantial Completion Date per Executed Change Order
| Actual Date of Substantial Completion: |  |  |  | The date on the Certificate of Substantial Completion.
8 | Schedule Variance: |  |  | 0 | This number will be automatically generated.
Was Client negatively impacted by schedule variance? (Yes/No)
Was schedule variance a result of other contractors? (Yes/No/Combined)
| COMMENTS: |  |  |  | Provide any written comments on the quantitative items regarding minimal or excessive number of changes or clarifications needed to complete the project per program.
SCORING LEGEND:
(5) Excellent; (4) Good; (3) Satisfactory; (2) Less than Satisfactory; (1) Unacceptable; (0) Not applicable |  |  |  |  | For each question asked, provide a 0-5 score based on the level of performance provided by the Contractor. If a 0 is used because the question does not apply to this project, then this question will not be included in the average score calculated below. (Typical for all Qualitative Questions)
Rank the five categories based on the criteria outlined in each one.
QUALITATIVE MEASUREMENTS: ("To what level…") |  |  |  | Score
Safety
1 | Did the Contractor submit and implement a project specific safety plan?
2 | Did the Contractor report any/all safety issues at every OAC meeting?
| SECTION SCORE: |  |  | 0
| SECTION AVERAGE SCORE: |  |  | 0
Schedule
1 | did the Contractor complete the post-award documentation (insurance forms, schedule of values, project schedule, etc) in a timely manner?
2 | did the Contractor turn in submittals in a timely manner?
3 | Was the Contractor effective in scheduling the work and organizing construction operations?
4 | did the Contractor comply with wage rates, labor laws and regulations indicated in the specifications (Diversity, Project Goals, etc.)?
5 | Did the Contractor submit regular updates to the schedule and revised progress schedules as appropriate?
6 | Did the Contractor have adequate equipment, tools and materials to maintain the project schedule?
7 | Did the Contractor have sufficient competent personnel to keep the project on schedule?
8 | Did the contractor cause any schedule delays to the project?
| SECTION SCORE: |  |  | 0
| SECTION AVERAGE SCORE: |  |  | 0
COORDINATION AND SUPERVISION:
1 | Was the Contractor represented at progress (OAC) meetings by a person with appropriate decision making authority?
2 | Did the Contractor work with the Client and Project Manager to maintain occupancy and traffic flow in areas impacted by remodeling, renovation and/or additions?
3 | Did the Contractor effectively manage other Prime Contractors, their own workforces and any sub‐contractors?
4 | did the Contractor coordinate work with the utilities and appropriately schedule any required outages?
5 | Did the Contractor submit the appropriate waivers as required by the Contract Documents?
| SECTION SCORE: |  |  | 0
| SECTION AVERAGE SCORE: |  |  | 0
Responsiveness
1 | Was the Contractor proactive in notifying the PSC and/or University of any deficiencies or problems with the Contract Documents?
2 | Did the Contractor proactivly work with the PSC to resolve any conflicts between conditions on‐site and the Contract Documents without additional cost or delays?
3 | Was the Contractor responsive and cooperative with the University client and Project Manager?
4 | Did the Contractor respond to RFP/CO's in a timely manner after receipt from the PSC?
| SECTION SCORE: |  |  | 0
| SECTION AVERAGE SCORE: |  |  | 0
PROJECT / FINAL CLOSEOUT
1 | Did the Contractor complete all punchlist items within the required timeline?
2 | Did the Contractor respond to warranty calls within a satisfactory time and completed work to resolve the issues?
3 | Did the Contractor provide closeout documentation (warranties, manuals, as-builts, etc) in a timely manner?
| SECTION SCORE: |  |  | 0
| SECTION AVERAGE SCORE: |  |  | 0
| TOTAL SCORE: |  |  | 0
| AVERAGE SCORE: |  |  | #DIV/0!
| COMMENTS: (Required for scores of less than 3) |  |  |  | Provide any written comments on those qualitative items that are scored less than a 3. Also, provide comments for those areas where the Contractor performed well.
RECOMMENDATIONS:
1 | Would you recommend contracting with this Contractor for future projects?
2 | Would you recommend contracting with the Contractor for projects with this budget range?
(Y) Yes; (N) No; (C) Conditional, would use Contractor again but with limitations listed below
| LIMITATIONS: |  |  |  | Provide your opinion on this Contractor. Would you want to work with them again? If so, are there any limitations (size of project, project type, person at the firm you enjoyed working with, etc.)
| LESSONS LEARNED: |  |  |  | Provide any lessons learned from completing this project to help others not make the same mistakes.

## export
Project RFPs/Change Orders: PSYCHOLOGY LABORATORY - RESTROOM RENOVATIONS (U20015)
RFP/Change Orders for Contract: E0023721
Vendor: AGAE Contractors Incorporated (@02676976)
Select Statuses:
Potential
Pending
Approved
Cancelled Show:
RFP Number | CO Number | Budget Reference | Description | Status | Type | Justification Code | Justification | Potential | Pending | Approved | Total
1 | 4 | 10600-4 | THE HOLLOW METAL DOOR FRAME HEAD DIMENSION NEEDS TO BE REVISED FROM 2" TO 4" TO ACCOMMODATE THE CMU WALL CONSTRUCTION. | APPROVED | LUMP SUM | PSC OMISSION | THE HOLLOW METAL DOOR FRAME HEAD DIMENSION NEEDS TO BE REVISED FROM 2" TO 4" TO ACCOMMODATE THE CMU WALL CONSTRUCTION. | 0 | 0 | 330.05 | 330.05
2 | 1 | 10600-1 | CURRIES MFG . DOOR FRAME EXPEDITE TO MEET THE SUMMER SCHEDULE. | APPROVED | LUMP SUM | DELIVERY/SCHEDULE | LONG LEAD TIME NEEDS TO BE EXPEDITED TO MEET SCHEDULE-4" HEAD SECTION CAUSED MANUFACTURER TO EXPEDITE THE MAKING OF THESE DOOR FRAMES. | 0 | 0 | 1025.51 | 1025.51
3 | 2 | 10600-2 | ROOM 46C NEEDS TO BE SECURED AT ALL TIMES FOR ITEMS STORED IN THE ROOM. | APPROVED | LUMP SUM | CLIENT REQUEST | CLIENT HAS REQUESTED THAT A DUST PROOF ENCLOSURE BE INSTALLED AT ROOM 46C WHICH NEEDS TO BE SECURED AT ALL TIMES FOR ITEMS STORED IN THE ROOM. | 0 | 0 | 564.29 | 564.29
4 | 3 | 10600-3 | THE USER REQUESTED ADDITIONAL FLOOR TILE REMOVAL AND NEW INSTALLATION AT THE GROUND FLOOR CORRIDOR. | APPROVED | LUMP SUM | CLIENT REQUEST | THE USER REQUESTED ADDITIONAL FLOOR TILE REMOVAL AND NEW INSTALLATION AT THE GROUND FLOOR CORRIDOR. | 0 | 0 | 9406.43 | 9406.43
6 | 6 | 10600-6 | WALL TO BE RE-UTILIZED WAS FOUND TO BE INFERIOR CLAY TILE. THIS ADDED COST IS TO BUILD A NEW CMU WALL AFTER THE CLAY TILE WALL IS DEMOLISHED. | APPROVED | LUMP SUM | UNFORESEEN CONDITIONS | DISCOVERED INFERIOR CLAY TILE WALL | 0 | 0 | 3136.04 | 3136.04
8 | 5 | 10600-5 | ADDED CONSTRUCTION COST TO REMOVE AND REPLACE RETURN AIR DUCT TO AHU5-IN JANITORS CLOSET TO ALLOW FOR ACCESS TO PLUMBING PIPES. | APPROVED | LUMP SUM | UNFORESEEN CONDITIONS | RETURN DUCT FROM AHU5 OVER JANITOR'S CLOSET DOES NOT ALLOW ACCESS TO PLUMBING PIPES. | 0 | 0 | 3361.13 | 3361.13
P005 | CO017 | 10600-19 | HIGHER SLAB LEVEL | APPROVED | LUMP SUM | PSC OMISSION | HIGHER SLAB LEVEL | 0 | 0 | 241.27 | 241.27
P009 | CO018 | 10600-20 | NEED TO RAISE SPRINKLER LINES TO BE ABOVE THE CEILINGS AT CORRIDOR C46 AND GROUND FLOOR MEN'S AND WOMEN'S RESTROOMS. | APPROVED | LUMP SUM | UNFORESEEN CONDITIONS | NEED TO RAISE SPRINKLER LINES TO BE ABOVE THE CEILINGS AT CORRIDOR C46 AND GROUND FLOOR MEN'S AND WOMEN'S RESTROOMS. | 0 | 0 | 146.74 | 146.74
P010 | CO007 | 10600-16 | NEED TO REVISE LAYOUT PER EXISTING PLUMBING PIPES TO REMAIN. | APPROVED | LUMP SUM | UNFORESEEN CONDITIONS | NEED TO REVISE LAYOUT PER EXISTING PLUMBING PIPES TO REMAIN. | 0 | 0 | 1867.02 | 1867.02
P013 | CO009 | 10600-7 | SEVERAL AREAS THAT NEED ADDITIONAL REMOVAL AND PATCHING AFTER DEMOLITION OF CERAMIC TILE AND WALLS. | APPROVED | LUMP SUM | PSC OMISSION | EXISTING MASONRY HAD TO BE REPLACED DUE TO POOR ORIGINAL CONSTRUCTION. | 0 | 0 | 10329.75 | 10329.75
P015 | CO030 | 10600-30 | AN EXISTING THERMOSTAT NEEDS TO BE RELOCATED NOT PREVIOUSLY SHOWN ON THE DRAWINGS. | APPROVED | LUMP SUM | UNFORESEEN CONDITIONS | TO MAINTAIN SCHEDULE | 0 | 0 | 1725.23 | 1725.23
P016 | CO022 | 10600-14 | PROVIDE ADDITIONAL CEILING ACCESS PANELS FOR EXISTING CONDITIONS, DEVICES AND CEILING ACCESS PER REQUEST OF UIUC INSPECTORS. PROVIDE AND INSTALL 4 NEW 18IN X 18IN ACCESS PANELS, RELOCATE EXISTING FRAMING TO ACCOMMODATE NEW ACCESS PANEL LOCATIONS AND AND PROVIDE AND INSTALL PLYWOOD. | APPROVED | LUMP SUM | STAFF CHANGES/SCOPE | PROVIDE ADDITIONAL CEILING ACCESS PANELS FOR EXISTING CONDITIONS, DEVICES AND CEILING ACCESS PER REQUEST OF UIUC INSPECTORS. | 0 | 0 | 4291.27 | 4291.27
P017 | 11 | 10600-27 | THE USER HAS REQUESTED THAT THE GYPSUM BOARD CEILING AT THE GROUND FLOOR MEN'S ROOM 0007, WOMEN'S ROOM 0001, ALL GENDER RESTROOMS ROOM 0040, 0044 AND 0046 BE CHANGED TO SUSPENDED ACOUSTICAL TILE CEILING TO AVOID THE MULTIPLE ACCESS PANELS THAT WOULD HAVE BEEN REQUIRED IN THE GYPSUM BOARD CEILING TO PROVIDE ACCESS TO ALL DEVICES. | APPROVED | LUMP SUM | STAFF CHANGES/SCOPE | THE USER HAS REQUESTED THAT THE GYPSUM BOARD CEILING AT THE GROUND FLOOR MEN'S ROOM 0007, WOMEN'S ROOM 0001, ALL GENDER RESTROOMS ROOM 0040, 0044 AND 0046 BE CHANGED TO SUSPENDED ACOUSTICAL TILE CEILING TO AVOID THE MULTIPLE ACCESS PANELS THAT WOULD HAVE BEEN REQUIRED IN THE GYPSUM BOARD CEILING TO PROVIDE ACCESS TO ALL DEVICES. | 0 | 0 | 20551.53 | 20551.53
P018 | CO014 | 10600-12 | DUE TO UNFORESEEN CONDITIONS, THE WALL AT ROOM 046, HAS MULTIPLE AREAS THAT NEED TO BE PATCH AND FILLED IN TO PROVIDE A FINISHED PAINTED FINISH. A LAYER OF ABUSE RESISTANT GYPSUM BOARD IS TO BE APPLIED TO THE EXISTING WALL AND PAINTED. | APPROVED | LUMP SUM | UNFORESEEN CONDITIONS | DUE TO UNFORESEEN CONDITIONS, THE WALL AT ROOM 046, HAS MULTIPLE AREAS THAT NEED TO BE PATCH AND FILLED IN TO PROVIDE A FINISHED PAINTED FINISH. | 0 | 0 | 2024.95 | 2024.95
P019 | CO013 | 10600-11 | PROVIDE CREDIT FOR LABOR AND MATERIALS TO INSTALL THE PAINTED GYPSUM BOARD CEILING AND PROVIDE AND INSTALLED NEW ACOUSTICAL CEILING TILE AND GRID AT ROOM 0342 AND 0348 AS SHOWN IN THE ATTACHED SKETCH. PATCH CEILING AT PERIMETER AS REQUIRED. | APPROVED | LUMP SUM | STAFF CHANGES/SCOPE | THE USER HAS REQUESTED TO CHANGE THE CEILING MATERIAL FROM PAINTED GYPSUM BOARD TO ACOUSTICAL TILE CEILING AT ROOMS 0342 AND 0348. | 0 | 0 | 2982.91 | 2982.91
P020 | CO012 | 10600-10 | THE DRAWINGS DID NOT INDICATE THE EXISTING CONDITIONS AT CORRIDOR C0040 AND THE VENDING AREA 0040A. THERE IS A CEILING HEIGHT DIFFERENCE THAT WILL REQUIRE A PAINTED GYPSUM BOARD SOFFIT. ADDITIONAL PLASTER PATCHING AND CEILING PATCHING IS REQUIRED AT WALLS AT THE CORRIDOR C0040 NEAR THE ALL GENDER TOILET ROOMS NOT SHOWN ON DRAWINGS. | APPROVED | LUMP SUM | PSC OMISSION | TO MAINTAIN CONSTRUCTION SCHEDULE | 0 | 0 | 8120.79 | 8120.79
P021 | CO015 | 10600-13 | DUE TO UNFORESEEN CONDITIONS, THE WEST WALLS AT THE MEN'S AND WOMEN'S RESTROOMS, THAT ARE TO BE PAINTED, NEED TO HAVE A LAYER OF ABUSE RESISTANT GYPSUM BOARD APPLIED TO PROVIDE A FINISHED WALL SURFACE FOR PAINTING. | APPROVED | LUMP SUM | UNFORESEEN CONDITIONS | TO MAINTAIN CONSTRUCTION SCHEDULE | 0 | 0 | 2024.95 | 2024.95
P022 | CO016 | 10600-15 | AT WEST WALLS OF ALL GENDER ROOMS 0040 AND 0044, THE DRAWINGS INDICATED PAINTED PLASTER WALLS. DUE TO UNFORESEEN CONDITIONS, AT 0044 THE WALL IS EXISTING CLAY TILE THAT DOES NOT PROVIDE AN ADEQUATE SURFACE FOR PLASTER. | APPROVED | LUMP SUM | UNFORESEEN CONDITIONS | MAINTAIN CONSTRUCTION SCHEDULE | 0 | 0 | 1244.72 | 1244.72
P023 | CO020 | 10600-17 | THE EAST WALL OF ROOMS 0040 AND 0044 WAS FOUND NOT TO EXTEND TO THE SLAB ABOVE, AND WITH THE ACOUSTICAL TILE CEILING INSTALLED, THERE WOULD BE NO SOUND SEPARATION FROM THE ALL GENDER RESTROOMS AND THE LAB ROOM. THE USER IS REQUESTING THAT THE WALL EXTEND TO THE THE SLAB ABOVE THE CEILING TO PROVIDE ACOUSTICAL SEPARATION. | APPROVED | LUMP SUM | UNFORESEEN CONDITIONS | TO MAINTAIN CONSTRUCTION SCHEDULE | 0 | 0 | 2108.65 | 2108.65
P024 | CO021 | 10600-18 | THE NORTH WALL OF THE WOMEN'S TOILET ROOM 0342 DOES NOT EXTEND TO THE BOTTOM OF THE SLAB. | APPROVED | LUMP SUM | UNFORESEEN CONDITIONS | MAINTAIN CONSTRUCTION SCHEDULE | 0 | 0 | 4017.95 | 4017.95
P025 | CO019 | 10600-21 | THE DRAWINGS DID NOT INDICATE THE REQUIRED REVISIONS TO THE SWITCHING OF THE LIGHTING, EXIT SIGNS AND FIRE ALARM REQUIRED WITH THE ADDITION OF THE PARTITION AND DOOR ADDED TO CORRIDOR C040. | APPROVED | LUMP SUM | PSC OMISSION | TO MAINTAIN SCHEDULE | 0 | 0 | 4089.75 | 4089.75
P026 | CO023 | 10600-22 | THE MECHANICAL DRAWINGS DID NOT INCLUDE THE TEMPERATURE CONTROL WORK TO INSTALL THE NEW MOTOR FOR THE EXHAUST FAN FOR THE NORTHEAST TOILET ROOMS.; ADDITIONAL WORK REQUIRED TO COMPLETE THE INSTALLATION OF THE NEW MOTOR REQUIRED FOR THE EXHAUST FAN INCLUDES:; MODIFYING TWO (2) EXISTING CONTROL CONDUITS AND COMPLETE CONTROL WIRING TERMINATIONS IN NEW FAN STARTER FOR EXISTING FAN EF 04 AT THE 9TH FLOOR MECHANICAL ROOM. ; DEMO OF EXISTING CONDUIT AND CONTROL CABLING FOR EF-4; INSTALL NEW CONDUIT AND CABLING TO NEW STARTER; TERMINATIONS | APPROVED | LUMP SUM | PSC OMISSION | THE MECHANICAL DRAWINGS DID NOT INCLUDE THE TEMPERATURE CONTROL WORK TO INSTALL THE NEW MOTOR FOR THE EXHAUST FAN FOR THE NORTHEAST TOILET ROOMS. | 0 | 0 | 1187.1 | 1187.1
P027 | CO024 | 10600-23 | THE USER HAS REQUESTED THAT THE FLOOR MATERIAL AT THE VENDING AREA BE REPLACED WITH THE NEW FORBO MARMOLEUM 20" X 20", NOT INCLUDED IN THE PREVIOUS CHANGE ORDER 003.; PROVIDE AND INSTALL NEW 20" X 20" AT VENDING AREA, 115 SQUARE FEET. | APPROVED | LUMP SUM | CLIENT REQUEST | THE USER HAS REQUESTED THAT THE FLOOR MATERIAL AT THE VENDING AREA BE REPLACED WITH THE NEW FORBO MARMOLEUM 20" X 20", NOT INCLUDED IN THE PREVIOUS CHANGE ORDER 003. | 0 | 0 | 1224.77 | 1224.77
P028 | CO025 | 10600-24 | INSTALLED TOILET PARTITIONS REQUIRE ADDITIONAL SUPPORT. | APPROVED | LUMP SUM | STAFF CHANGES/SCOPE | TO MAINTAIN CONSTRUCTION SCHEDULE | 0 | 0 | 3839.78 | 3839.78
P029 | CO028 | 10600-25 | THE ARCHITECTURAL DRAWINGS MISSED THE KEY NOTE TO IDENTIFY AN ELECTRIC HAND DRYER AT THE THIRD FLOOR WOMEN'S RESTROOM | APPROVED | LUMP SUM | PSC OMISSION | TO MAINTAIN CONSTRUCTION SCHEDULE | 0 | 0 | 832.3 | 832.3
P030 | CO027 | 10600-26 | THE EXISTING FIRE ALARM HANDSET NOT SHOWN ON DRAWINGS TO BE REMOVED AND REINSTALLED IN NEW WALL. | APPROVED | LUMP SUM | PSC OMISSION | TO MAINTAIN CONSTRUCTION SCHEDULE | 0 | 0 | 501.53 | 501.53
P031 | CO026 | 10600-28 | AT THE CORRIDOR AT THE THIRD FLOOR THERE IS AN EXISTING CABLE TRAY THAT IS SUPPORTED OFF OF THE WALL THAT WAS DEMOLISHED AND REQUIRES TO BE SUPPORTED TO NEW INSTALLED CMU WALL. | APPROVED | LUMP SUM | UNFORESEEN CONDITIONS | MAINTAIN CONSTRUCTION SCHEDULE | 0 | 0 | 1774.74 | 1774.74
P032 | CO029 | 10600-29 | THE EXISTING TRANSFER GRILLE NEEDS TO HAVE A SIGHT PROOF VENT INSTALLED. | APPROVED | LUMP SUM | STAFF CHANGES/SCOPE | TO MAINTAIN CONSTRUCTION SCHEDULE | 0 | 0 | 957.47 | 957.47
P035 | CO031 | 10600-33 | ORIGINAL SCOPE:; AT MEN'S TOILET ROOM 07, WOMEN'S TOILET ROOMS 01 AND 344: REPLACE THE EXISTING TOILET PARTITION PILASTERS PER ASK 10-11, RFP 28.; UPDATE:; GLOBAL SUPPLY DOES NOT PROVIDE A PILASTER WITH HEADRAIL AT 7'-0".; THE UPDATED PILASTERS HAVE A HEADRAIL WITH MAXIMUM CLEARANCE OF 6'-9" BELOW THE RAILS.; THERE IS AN INCREASE IN MATERIAL COSTS ABOVE THE APPROVED RFP 28/CO 25. | APPROVED | LUMP SUM | STAFF CHANGES/SCOPE | REPLACE TOILET PARTITION PILASTERS. | 0 | 0 | 1296.63 | 1296.63
P036 | CO033 | 10600-34 | DEMOLITION AND DOOR OPENING MODIFICATIONS HAD TO BE PERFORMED FOR THE ALL GENDER RESTROOM DUE TO UNFORESEEN DOOR FRAME AND WALL CONNECTIONS. THE FRAMERS WERE ORDERED BEFORE THE CONDITION WAS DISCOVERED AND MODIFIED IN THE FIELD. | APPROVED | LUMP SUM | UNFORESEEN CONDITIONS | ALL GENDER RESTROOM DOOR OPENING MODIFICATION | 0 | 0 | 3136.38 | 3136.38
P037 | CO034 | 10600-35 | PLANS INDICATED THAT EXISTING EXHAUST FAN POWER WAS 480V, POWER VERIFIED IN FIELD TO BE 120V. CHANGE FOR WORK RELATED TO CONVERT TO 480V POWER. | APPROVED | LUMP SUM | PSC OMISSION | EXHAUST FAN POWER CONVERSION: 120V TO 480V | 0 | 0 | 1843.86 | 1843.86
P038 | CO035 | 10600-36 | REMOVE AND REINSTALL EXISTING DUCTWORK TO ALLOW FOR CMU WALL INSTALLATION ON THE THIRD FLOOR NEAR THE DRINKING FOUNTAIN. FIELD CONDITION DISCOVERY. | APPROVED | LUMP SUM | UNFORESEEN CONDITIONS | ADJUST DUCTWORK FOR CMU WALL INSTALLATION | 0 | 0 | 3516.11 | 3516.11
P039 | CO036 | 10600-37 | INCREASED CMU AND PLASTER DEMOLITION TO ACCOMMODATE ASK-01 FOR ALL-GENDER RESTROOMS. INCREASED FLOOR PREP IN ALL-GENDER RESTROOMS - THE DEMOLITION CREATED FLOOR CAVITIES THAT NEEDED TO FILLED/REPAIRED. | APPROVED | LUMP SUM | UNFORESEEN CONDITIONS | PLASTER DEMO & FLOOR PREP AT ALL-GENDER RESTR | 0 | 0 | 4869.53 | 4869.53
RFP 007 | CO 010 | 10600-8 | THE EXISTING FLOOR DRAIN AT THE VENDING AREA CAN REMAIN. NO NEW WATER LINE IS REQUIRED. PROVIDE A CREDIT FOR THE WORK DESCRIBED ON P101, FOR WORK NOT REQUIRED. SUMMARIZED BELOW. ¿ EXISTING ¾¿ CW DROP TO REMAIN ¿ EXISTING FLOOR DRAIN TO REMAIN ¿ NO SAW CUTTING OF SLAB REQUIRED FOR NEW DRAIN ¿ NO NEW ¾¿ CW LINE REQUIRED FOR VENDING MACHINES ¿ NO NEW FD REQUIRED AND NO NEW VENT | POTENTIAL | LUMP SUM | PSC OMISSION | CREDIT FOR WORK NOT REQUIRED. | 0 | 0 | 0 | 0
RFP 011 | CO 008 | 10600-31 | A HARD CEILING NEEDS TO BE DEMOLISHED THAT WAS NOT SHOWN ON THE DRAWINGS AT THE NEW DOOR TO THE WORK ROOM AT THE GROUND FLOOR. | APPROVED | LUMP SUM | PSC OMISSION | THE BID DOCUMENTS DID NOT SHOW THIS WORK ON THE DRAWINGS. | 0 | 0 | 1778.96 | 1778.96
Total Changes: | [7 empty] | 0 | 0 | 110350.09 | 110350.09

## export (2)
CO # | Contractor | Division of Work | Brief Description | Classification | Amount | Contract Number | Date | Ready for Approval | CBM Approval
1 | AGAE Contractors Inc. | Division 01 - General Work | Long lead time needs to be expedited to meet schedule | Delivery/Schedule | 1025.51 | E0023721 | 2021-07-01 | Yes | Yes
2 | AGAE Contractors Inc. | Division 01 - General Work | Room 46C needs to be secured at all times for items stored in the room. | Client Request | 564.29 | E0023721 | 2021-07-01 | Yes | Yes
3 | AGAE Contractors Inc. | Division 01 - General Work | The user requested additional floor tile removal and new installation at the ground floor corridor. | Unforeseen Conditions | 9406.43 | E0023721 | 2021-07-01 | Yes | Yes
4 | AGAE Contractors Inc. | Division 01 - General Work | Revise hollow metal head detail | PSC Omission | 330.05 | E0023721 | 2021-07-01 | Yes | Yes
5 | AGAE Contractors Inc. | Division 01 - General Work | Existing ductwork in the way to get access to plumbing pipes | Unforeseen Conditions | 3361.13 | E0023721 | 2021-07-08 | Yes | Yes
6 | AGAE Contractors Inc. | Division 01 - General Work | During demolition the wall where the existing plumbing pipes for the sink to be removed was found to be a clay tile wall at the ground floor existing locker room. | Unforeseen Conditions | 3136.04 | E0023721 | 2021-07-08 | Yes | Yes
7 | AGAE Contractors Inc. | Division 01 - General Work | Need to revise layout per existing plumbing pipes to remain. | Unforeseen Conditions | 1867.02 | E0023721 | 2021-07-20 | Yes | Yes
8 | AGAE Contractors Inc. | Division 01 - General Work | A hard ceiling needs to be demolished that was not shown on the drawings at the new door to the Work Room at the Ground Floor. | PSC Omission | 1778.96 | E0023721 | 2021-07-26 | Yes | Yes
9 | AGAE Contractors Inc. | Division 01 - General Work | Several areas that need additional removal and patching after demolition of ceramic tile and walls. | PSC Omission | 10329.75 | E0023721 | 2021-07-30 | Yes | Yes
10 | AGAE Contractors Inc. | Division 01 - General Work | Plumbing work at Vending Machines | PSC Omission | -1983.45 | E0023721 | 2021-08-09 | Yes | Yes
11 | AGAE Contractors Inc. | Division 01 - General Work | The user has requested that the gypsum board ceiling at the Ground Floor Men's Room 0007 Women's Room 0001 All Gender Restrooms Room 0040 0044 and 0046 be changed to suspended acoustical tile ceiling to avoid the multiple access panels that would have been required in the gypsum board ceiling to provide access to all devices. | Staff Changes/Scope | 21612.03 | E0023721 | 2021-08-10 | Yes | Yes
12 | AGAE Contractors Inc. | Division 01 - General Work | The drawings did not indicate the existing conditions at corridor C0040 and the vending area 0040A. There is a ceiling height difference that will require a painted gypsum board soffit. Additional plaster patching and ceiling patching is required at walls at the corridor C0040 near the All Gender Toilet Rooms not shown on drawings. | PSC Omission | 8120.79 | E0023721 | 2021-08-26 | Yes | Yes
13 | AGAE Contractors Inc. | Division 01 - General Work | The user has requested to change the ceiling material from painted gypsum board to acoustical tile ceiling at Rooms 0342 and 0348. | Staff Changes/Scope | 2982.91 | E0023721 | 2021-08-26 | Yes | Yes
14 | AGAE Contractors Inc. | Division 01 - General Work | Due to unforeseen conditions the wall at Room 046 has multiple areas that need to be patch and filled in to provide a finished painted finish. | Unforeseen Conditions | 2024.95 | E0023721 | 2021-08-26 | Yes | Yes
15 | AGAE Contractors Inc. | Division 01 - General Work | Due to unforeseen conditions the west walls at the Men's and Women's restrooms that are to be painted need to have a layer of abuse resistant gypsum board applied to provide a finished wall surface for painting. | Unforeseen Conditions | 2024.95 | E0023721 | 2021-08-30 | Yes | Yes
16 | AGAE Contractors Inc. | Division 01 - General Work | At west walls of All Gender Rooms 0040 and 0044 the drawings indicated painted plaster walls. Due to unforeseen conditions at 0044 the wall is existing clay tile that does not provide an adequate surface for plaster. | Unforeseen Conditions | 1244.72 | E0023721 | 2021-09-08 | Yes | Yes
17 | AGAE Contractors Inc. | Division 01 - General Work | Higher slab level | PSC Omission | 5066.67 | E0023721 | 2021-09-23 | Yes | Yes
18 | AGAE Contractors Inc. | Division 01 - General Work | Need to raise sprinkler lines to be above the ceilings at Corridor C46 and Ground Floor Men's and Women's Restrooms. | Unforeseen Conditions | 3081.49 | E0023721 | 2021-09-23 | Yes | Yes
19 | AGAE Contractors Inc. | Division 01 - General Work | The drawings did not indicate the required revisions to the switching of the lighting exit signs and fire alarm required with the addition of the partition and door added to Corridor C040. | PSC Omission | 4089.75 | E0023721 | 2021-09-29 | Yes | Yes
20 | AGAE Contractors Inc. | Division 01 - General Work | The east wall of Rooms 0040 and 0044 was found not to extend to the slab above and with the acoustical tile ceiling installed there would be no sound separation from the All Gender Restrooms and the Lab Room. The user is requesting that the wall extend to the the slab above the ceiling to provide acoustical separation. | Unforeseen Conditions | 2108.65 | E0023721 | 2021-09-29 | Yes | Yes
21 | AGAE Contractors Inc. | Division 01 - General Work | The north wall of the Women's Toilet Room 0342 does not extend to the bottom of the slab. | Unforeseen Conditions | 4017.95 | E0023721 | 2021-09-29 | Yes | Yes
22 | AGAE Contractors Inc. | Division 01 - General Work | Provide additional ceiling access panels for existing conditions devices and ceiling access per request of UIUC inspectors. | Staff Changes/Scope | 4291.27 | E0023721 | 2021-09-29 | Yes | Yes
23 | AGAE Contractors Inc. | Division 01 - General Work | The mechanical drawings did not include the temperature control work to install the new motor for the Exhaust Fan for the Northeast Toilet Rooms. | PSC Omission | 1187.1 | E0023721 | 2021-10-05 | Yes | Yes
24 | AGAE Contractors Inc. | Division 01 - General Work | The user has requested that the floor material at the vending area be replaced with the new Forbo Marmoleum 20" x 20" not included in the previous Change Order 003. | Client Request | 1224.77 | E0023721 | 2021-10-06 | Yes | Yes
25 | AGAE Contractors Inc. | Division 01 - General Work | Installed toilet partitions require additional support. | Staff Changes/Scope | 3839.78 | E0023721 | 2021-10-29 | Yes | Yes
26 | AGAE Contractors Inc. | Division 01 - General Work | At the corridor at the third floor there is an existing cable tray that is supported off of the wall that was demolished and requires to be supported to new installed CMU wall. | Unforeseen Conditions | 1774.74 | E0023721 | 2021-11-04 | Yes | Yes
27 | AGAE Contractors Inc. | Division 01 - General Work | The existing fire alarm handset not shown on drawings to be removed and reinstalled in new wall. | PSC Omission | 501.53 | E0023721 | 2021-11-04 | Yes | Yes
28 | AGAE Contractors Inc. | Division 01 - General Work | The architectural drawings missed the key note to identify an electric hand dryer at the third floor Women's Restroom | PSC Omission | 832.3 | E0023721 | 2021-11-04 | Yes | Yes
29 | AGAE Contractors Inc. | Division 01 - General Work | The existing transfer grille needs to have a sight proof vent installed. | Staff Changes/Scope | 957.47 | E0023721 | 2021-11-23 | Yes | Yes
30 | AGAE Contractors Inc. | Division 01 - General Work | An existing thermostat needs to be relocated not previously shown on the drawings. | Unforeseen Conditions | 1725.23 | E0023721 | 2021-12-14 | Yes | Yes
31 | AGAE Contractors Inc. | Division 01 - General Work | Replace toilet partition pilasters. | Staff Changes/Scope | 1296.63 | E0023721 | 2022-03-30 | Yes | Yes
32 | AGAE Contractors Inc. | Division 01 - General Work | Install wood doors at doors 40A 40B and 344 | Client Request | 0 | E0023721 | 2022-03-30 | Yes | Yes
33 | AGAE Contractors Inc. | Division 01 - General Work | All Gender restroom door opening modification | Unforeseen Conditions | 3136.38 | E0023721 | 2022-07-11 | Yes | Yes
34 | AGAE Contractors Inc. | Division 01 - General Work | Exhaust Fan power conversion: 120V to 480V | PSC Omission | 1843.86 | E0023721 | 2022-07-11 | Yes | Yes
35 | AGAE Contractors Inc. | Division 01 - General Work | Adjust ductwork for CMU wall installation | Unforeseen Conditions | 3516.11 | E0023721 | 2022-07-11 | Yes | Yes
36 | AGAE Contractors Inc. | Division 01 - General Work | Plaster Demo & Floor Prep at all-gender Restr | Unforeseen Conditions | 4869.53 | E0023721 | 2022-07-11 | Yes | Yes